## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | BH, Oct 19 | Pass | AH, Nov 3
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | BH, Oct 19 | Pass | AH, Nov 3
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Fail | BH, Oct 19, forgot to display alongside product images within the products page, need to be implemented on products page on top of product details page | Pass | AH, Nov 3, and BH, Nov 7, originally failed due to not having visual for out of stock products, fixed by displaying an out of stock image
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | BH, Oct 19 | Pass | AH, Nov 3
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | BH, Oct 19 | Pass | AH, Nov 3
As a CUSTOMER I want to BE ABLE TO SEARCH FOR A PRODUCT so that I DO NOT HAVE TO SCROLL ALL OVER THE WEBSITE TO FIND A SPECIFIC ITEM. | **Given** THE SEARCH WORKS **when** I USE THE SEARCH BAR **then** I EXPECT THE ITEM I'M SEARCHING FOR TO COME UP. | Pass | BH, Oct 19 | Pass | AH, Nov 3, and BH, Nov 7, originally failed due to routing that didn't use the name in the url, now fixed
As a buyer I want the functionality to log into my account so that I can add/view items in the inventory/shopping cart. | **Given** the users account exists **when** I type in their username and press log in **then** I expect for the estore to display the saved shopping cart | Fail | BH, Oct 19, no backend file system for users and shopping cart to be saved to, needs to be implemented in next sprint | Pass | AH, Nov 3
| **Given** the users account doesn't exist **when** I type in a username and press log in **then** I expect for the estore to display an empty shopping cart | Pass | BH, Oct 19 | Pass | AH, Nov 3
| **Given** the users account doesn't exist **when** I type in a username and press log in **then** I expect for a new account to be made | Fail | BH, Oct 19, no backend file system for users and shopping cart to be saved to, needs to be implemented in next sprint | Pass | AH, Nov 3
| **Given** the users account exists **when** I type in a username and press log in **then** I expect for the saved shopping cart to be fetched | Fail | BH, Oct 19, no backend file system for users and shopping cart to be saved to, needs to be implemented in next sprint | Pass | AH, Nov 3
As a buyer I want the functionality for to log out of my account so that another user can log in and have an empty shopping cart. | **Given** the estore page is up **when** I click the log out button **then** I expect for the log in page to appear | Pass | BH, Oct 19 | Pass | AH, Nov 3
| **Given** the estore page is up **when** I click the log out button **then** I expect the user's shopping cart and username to be stored | Fail | BH, Oct 19, no backend file system for users and shopping cart to be saved to, needs to be implemented in next sprint | Pass | AH, Nov 3
As a ADMIN I want to add a product to the inventory so that users can add it to their shopping cart. | **Given** inventory exists **when** I add a product **then** I expect the product to be added to the inventory. | Pass | BH, Oct 19 | Pass | AH, Nov 3
| **Given** inventory exists **when** I add a product **then** I expect the product to be displayed on the inventory page. | Pass | BH, Oct 19 | Pass | AH, Nov 3
As an admin I want to be able to update products so that I can change products in the store without having to delete them and make a new one. | **Given** the product exists **when** I update it **then** the product's data should be changed | Pass | BH, Oct 19 | Pass | AH, Nov 3
| **Given** the product exists **when** I update it **then** the product's page should appear differently | Pass | BH, Oct 19 | Pass | AH, Nov 3
As a Admin I want to submit a request to delete a single product SO THAT it is no longer in the inventory. | GIVEN I submit a product object WHEN the product with the given id exists in the inventory THEN the system should delete the product from the inventory, save to the persistent store, and return a status code of 204 (NO CONTENT) | Pass | BH, Oct 19 | Pass | AH, Nov 3
| Given I submit a product object WHEN the product with the given id does not exist in the inventory THEN the system should return a status code of 404 (NOT FOUND) | Pass | BH, Oct 19 | Pass | AH, Nov 3
As an ADMIN I want to BE ABLE TO VIEW THE INVENTORY so that I CAN CHECK THAT THE STORE'S INVENTORY IS UP TO DATE AND ACCURATE. | **Given** the inventory exists and isn't empty **when** view the inventory **then** I expect to see every product inside of it with all attributes correct | Pass | BH, Oct 19 | Pass | AH, Nov 3
As a buyer I want to view a product so that I can view the details of the selected product. | **Given** the inventory has items in it **when** I select a product in the inventory **then** I should be able to see all of the selected product's details | Pass | BH, Oct 19 | Pass | AH, Nov 3
As a buyer I want to be able to add and remove items from my shopping cart so that i can purchase products and change my mind if I no longer want them. | **Given** the product is available in the store **when** I click the add product button and specify the number of products **then** the product and quantity to shop up in my cart. | Pass | BH, Oct 19 | Pass | AH, Nov 3
| **Given** the product is in my shopping **when** I click the remove button on the product **then** the item should no longer appear in my cart | Pass | BH, Oct 19 | Pass | AH, Nov 3
As an owner, I want to create coupons in the e-store that can be used for different products so that users can have discounts. | **Given** I am logged in as the owner **when** I navigate to the coupon page **then** I am presented with a form to add a coupon | Fail | BH, Oct 19, unimplemented and intended for sprint 3 | Fail | BH, Nov 7, there is no page for coupons for the admin and no way to add a coupon directly within the website
| **Given** I am logged in as the owner **when** I add a coupon **then** users can now apply that coupon in the shopping cart for discounts. | Fail | BH, Oct 19, unimplemented and intended for sprint 3 | Pass | BH, Nov 7
| **Given** I am logged in as the owner **when** I navigate to the coupon page **then** I am presented with a list of coupons to update/delete | Fail | BH, Oct 19, unimplemented and intended for sprint 3 | Fail | BH, Nov 7, there is no page for coupons for the admin and no way to see the list of coupons directly within the website
As a team member, I must make sure that coupons actually take off prices whenever they are applied by users. | **Given** I apply a coupon **when** I have applicable products in the shopping cart **then** the applicable products should be discounted | Fail | BH, Oct 19, unimplemented and intended for sprint 3 | Pass | BH, Nov 7
| **Given** the coupon code is valid and applies to products **when** I apply it to the cart **then** I see the new price of the products | Fail | BH, Oct 19, unimplemented and intended for sprint 3 | Pass | BH, Nov 7